## Sheet1
Regional Statistical Development Program Monitoring Form |  |  |  |  | RSDP Form 3 (Monitoring Form)
Region: Cordillera Administrative Region (CAR)
Statistical Development Program/Project/Activity |  | Target Date of Implementation (per RSDP) | Lead/ Implementing Agencies | Status* | Remarks/Plans (e.g., if ongoing or not implemented)
1. Coordination of the Regional Statistical System (RSS)
Social and Demography
1 | Regional Data Reconciliation and Technical Working Group Meeting | 2017 onwards | DOH |  | Conducted TWG Meeting on September 11 - 13, 2018 and Data Reconciliation Activties per province/ City on February 2018
2 | Quarterly Meeting on Health Sector Performance Monitoring and Evaluation System (HSPMES | 2017 onwards | DOH
Economic
3 | Roll-out of the Enhanced Client Profile and Monitoring System (e-CPMS) | Test run Q3 2017 | DTI
4 | Full adoption of the Local Tourism Statistics System (LTSS) by the Local Government Units (Municipal level) Policy | Monthly/ Quarterly | DOT |  | selected municipalities adopted the LTSS
Multi-domain
5 | Quarterly Meeting of the Regional Statistics Committee | 2017 onwards Quarterly | RSC |  | 4 regular RSC meetings conducted;
6 | Environment and Natural Resources Accounting (ENRA) Project Team and Steering Committee | 2017 onwards | PSA |  | 7 meetings conducted by the Project Team
7 | Regional Technical Committee on Survey Design (RTCSD) | 2017 onwards | PSA |  | Census on Buildings/Structures in Baguio City with PSA No. CBAO baguio-1847 received on August 28, 2018
8 | Creation and Convening Regular Provincial Statistics Committee meeting | 2017 onwards | LGU Mt. Province LGU Ifugao |  | In addition,the provincial government of Benguet, Abra, and Kalinga were able to create and establish their Provincial Statistics Committee Meeting last year Ifugao PSC conducted 4 PSC meetings on the ff dates Jan 30, May 3, Sept 5 & Dec 13, 2018
2. Data Collection/ Production
Social and Demography
9 | Survey on Level Stakeholders’ Satisfaction with NAPOLCOM Plans, programs and Policy Advisory | last quarter of every year (2018 onwards) | NAPOLCOM |  | Survey conducted on Nov 23, 2018 to 163 respondents (48 Police Commissioned Officers and 115 Police Non-Commissioned Officers)
10 | Updating of the List of Establishments | 2017 onwards Annual | PSA |  | continuing survey; annual
11 | Annual Survey of the Philippine Business and Industry (ASPBI) | 2017 onwards Annual | PSA |  | continuing survey; annual
12 | Labor Force Survey (LFS) | 2018 onwards Quarterly | PSA |  | 4 surveys conducted in 2018 ( Q4 2017 , Q1 2018, Q2 2018, Q3 2018)
13 | Consumer Price Index (CPI) | 2018 onwards Monthly | PSA |  | continuing survey
14 | National Demographic and Health Survey | 2017 onwards Every 5 years | PSA |  | implemented in 2017
15 | Generation of Vital Statistics form the Civil Registration System | 2017 onwards | DOH
16 | Vital Statistics | 2017 onwards | PSA |  | continuing
17 | Functional Literacy, Education and Mass Media Survey (FLEMMS) | 2019 | PSA |  | to be conducted in 2019
18 | Population Census (POPCEN) | 2020 | PSA |  | to be conducted in 2019
19 | 2020 Census of Population and Housing (CPH) | 2020 | PSA |  | to be conducted in 2019
20 | 2016 Model Functioning Survey (MFS) | 2019 | PSA |  | implemented in 2017 and to be conducted in 2020
21 | Enhanced Basic Education Information System (EBEIS), Learners Information System (LIS) including Alternative Learning System (ALS) | 2017 onwards | DEPED
22 | CHED Electronic collection and knowledge system (CHECKS) | June – September Annual | CHED
23 | Barangay Skills Needs Survey | 2017 onwards | TESDA |  | There were 841 barangays surveyed in CAR.
24 | Unified TVET program Registration and Accredited System | 2018 onwards Monthly | TESDA |  | Continuously implemented. For 2018 UTPRAS Accomplishment: 60 New Programs Registered; 6 Number of STAR rated programs/APACC accreditation recognized ; 100% of registered accredited TVET programs audited.
25 | Management Information System/ TESDA Training and Monitoring Information System (T2MIS) | 2018 onwards Monthly | TESDA |  | Continuously updated. T2MIS is the centralized TESDA database. In 2018, workshop was done for the focals to be abreast with the system.
26 | Seal of Good Local Governance (SGLG) | 2017 onwards April to October | DILG
27 | Full Disclosure Policy (FDP) | 2018 onwards Quarterly | DILG
28 | Philippine Indigenous Peoples Ethnographies (PIPE) | 2017-2022 | NCIP |  | This survey did not materialize however NCIP Cordillera is pushing for the conduct of its own survey called CIPE survey based on the methodology of PIPE. NCIP is lobbying for budget.
29 | Community-based Monitoring System(CBMS) | 2015-2018 | LGU Benguet
30 | Community-based Monitoring System(CBMS) | 2016-2017 | LGU Ifugao |  | finalized and printed the 2016 Poverty Map of Ifugao based on the CBMS result
31 | Generation of 2017 LGU Health Scorecard Results | 2018 | DOH |  | Additional
32 | Generation of Epidemiological and Surveillance Data | 2017 onwards | DOH |  | Additional
Economic
33 | Negosyo Center Project Management Report (NCPMR) | Monthly (2017), Annual (2015 onwards) | DTI
34 | Business Permits and Licensing System (BPLS) | 2012 onwards Annual | DTI
a. BPLS Customer Experience Survey for Renewal of Business Permit
| b. BPLS Field Monitoring and Evaluation Survey |  |  |  | Activity was cancelled per instruction of the Competitiveness Bureau of DTI, to focus on the RA 11032 or the Ease of Doing Business
35 | Philippine Business Registry System (PBR) | Monthly 2012 onwards | DTI
36 | Online Price Monitoring System (OPMS or e-Presyo) | Monthly except Baguio and Benguet (weekly) 2016 onwards | DTI
37 | Industry Cluster Project | Q4 2017 to 2018 (Updating of 2015 Profiles) | DTI
38 | Economic Zone Monitoring Performance Reports | Monthly, Qtr, Semi-Annual, Annual 2017 onwards | PEZA
39 | Communication Plan for Minerals Development-Statistical Reporting System | 2017-2022 | MGB
40 | Mineral Resources and Geosciences Reports | 2017-2023 | MGB
41 | Convergence program under DOT and DPWH statistics | 2017 onwards | DPWH
42 | GRDP Estimation | 2017 onwards Annual | PSA |  | continuing activity of PSA
43 | Backyard and Livestock Production Survey (BLPS) | 2017 onwards | PSA |  | continuing survey of PSA
44 | Crops Production Survey | 2017 onwards | PSA |  | continuing survey of PSA
45 | Farm Price Survey | 2017 onwards | PSA |  | continuing survey of PSA
46 | Monthly Palay and Corn Situation Report (MPCSR) | 2017 onwards | PSA |  | continuing survey of PSA
47 | Fishery Production Survey | 2017 onwards | PSA |  | continuing survey of PSA
48 | Palay and Corn Production Survey (PCPS) | 2017 onwards | PSA |  | continuing survey of PSA
49 | Palay and Corn Stock Survey | 2017 onwards | PSA |  | continuing survey of PSA
50 | Survey on Information and Communication Survey (SICT) | 2017 onwards | PSA
51 | Foreign Trade Statistics | 2017 onwards | PSA |  | continuing survey of PSA
52 | Consumer Price Index (CPI) | 2017 onwards | PSA |  | continuing survey of PSA
53 | Household Survey on Domestic Visitors (HSDV) | 2017 onwards | PSA |  | to be conducted in 2019
54 | Feasibility study preparation |  | LGU-Mt. Prov |  | to be conducted in other years
55 | Status report of Irrigation development | 2017 onwards Annual | NIA
56 | Annual Inventory of NIS/CIS | 2017 onwards Annual | NIA
57 | Conduct of Business Expectations Survey | quarterly | BSP
58 | Compendium on Science and Technology | 2017 -onwards Biennial | DOST |  | The finalization 2017 Compendium on S&T still on going
59 | BSP Knowledge Resource Network | 2017 onwards | BSP
60 | Banking Statistics (Fact Book) | 2018 onwards | BSP
61 | Internal Revenue Allotment (IRA) shares of LGUs | April – June Annual | DBM
62 | Consolidated tax collections and analyzed drastic changes of collection performance against goal and previous year’s period collection | 2017 onwards monthly | BIR
63 | Cooperative Registration Information System (COOPRIS) | 2017 onwards | CDA
64 | Cooperative Annual Progress Report Information System (CAPRIS) | 2018 onwards | CDA
65 | Cities and Municipalities Competitiveness Index (CMCI) Survey | 2017 onwards | DTI |  | Survey is done annually
66 | Labor Turnover Survey (LTS) | 2018 | PSA |  | LTS was expanded to all regions in 2018; 3 survey rounds (Q1, Q2,Q3) were conducted in 2018; Q4 survey round started this March 2019
Multi-domain
67 | Annual Poverty Indicators Survey | 2017 onwards annual | PSA |  | APIS was not conducted in 2018 because of the conduct of 2018 FIES. Scheduled to be conducted in 2019
68 | Family Income and Expenditure Survey | 2018 onwards Every 3 years | PSA |  | Collection of data started in 2nd semester of 2018 and continued in first sem of 2019
69 | Provincial Socio-economic Profile | Jan- Dec Every 5 years | LGU Mt. Prov & Beng |  | On-going
70 | CAR Philippine Indigenous Peoples Ethnographies (PIPE) | 2017-2022 | NCIP |  | renamed to CIPES survey; to be conducted once fund is available
71 | Community-based Monitoring System(CBMS) | 2015-2018 | LGU Benguet
72 | Community-based Monitoring System(CBMS) | 2016-2017 | LGU Ifugao |  | finalized and printed the 2016 Poverty Map of Ifugao based on the CBMS result
73 | Environment and Natural Resources Accounting Estimation | 2017 onwards | PSA |  | Mineral Accounting of CAR started in 2018 and continued up to 2019
3. Data Dissemination and Use
Social and Demography
74 | Reproduction and dissemination of crime prevention flyers | July – August Annual | NAPOLCOM |  | 3,000 pcs flyers; 800 pcs whistles
75 | Reproduction and dissemination of Primer on Police Benefits | July – August | NAPOLCOM |  | 200 pcs flyers
76 | Maintenance of Social Network sites and Regional Government Network | Year Round | NAPOLCOM |  | 2 Facebook Fun Pages
77 | Maintenance of Online RPFP (Responsible Parenthood and Family Planning) Monitoring System | 2012- up to present Monthly | POPCOM |  | on-going
78 | Quarterly Statwatch | Jan – Dec Quarterly | LGU – Baguio City |  | gathered for quarterly statwatch
79 | Social Protection Research Forum | Annual | DSWD |  | Conducted on 25 December 2018 which was attended by 70 (21 male and 49 female) participants
80 | National Demographic and Health Survey Regional Dissemination Workshop | 2018 | PSA |  | Conducted on November 9, 2018 which was attended by 80 participants; new activity
Economic
81 | Online Price Monitoring System (OPMS or e-Presyo) | Monthly except Baguio and Benguet (weekly) 2016 onwards | DTI |  | Except for 2 CAR provinces in 2017 due to very poor internet connectivity- Abra and Kalinga
82 | Industry Cluster Project | Q4 2017 to 2018 (Updating of 2015 Profiles) | DTI |  | Continuing project of the Department
83 | PEZA-BCEZ Presentation Materials | Monthly updates 2017-2022 | PEZA
84 | Compendium on Science and Technology | 2017 -onwards Biennial | DOST |  | The finalization 2017 Compendium on S&T still on going
85 | GRDP News Conference | 2017 | PSA |  | 2015-2017 Gross Regional Domestic Product (GRDP) was conducted on April 26, 2018
86 | ASPBI Respondent's Forum | 2017 | PSA |  | Conducted on May 31, 2018 at Prince Plaza Hotel, Baguio City
87 | SICT/ISLE Respondent's Forum | 2018 | PSA |  | Conducted on September 7, 2018 in Baguio City; new activity
88 | 2015 Census on Population Dissemination | 2017 | PSA |  | conducted in 2017
89 | Special Releases, Press Releases, News Letter | 2017 | PSA |  | 50 special releases, 4 newsletters, and 7 press releases
90 | National Statistics Month Celebration | 2017 onwards | PSA RLAs LGUs SUCs |  | 209 activities were coordinated and conducted in the region
91 | Building Provincial Database and Information | 2019-2020 | LGU Mt. Province |  | On-going
92 | Banking Statistics (Fact Book) | Annual 2017 onwards | BSP
93 | Dissemination of Agriculture and Fisheries Data | 2018-2022 | DA
94 | Quarterly Statwatch | Jan – Dec Quarterly | LGU – Baguio City
95 | Research Forums | SY 2017-2018 (once) | CHED
96 | Establishment of Facebook account for CAR statistics quarterly submission | 3rd Quarter of 2017-2022 | DOT
97 | Cities and Municipalities Competitiveness Index (CMCI) Awarding | 2017 onwards | DTI |  | Awarding is done annually
Multi-domain
98 | Special Releases, Press Releases, News Letter | 2017 | PSA
99 | Provincial Socio-economic Profile | Jan- Dec Every 5 years | LGU Mt. Province & Benguet |  | On-going
100 | Building Provincial Database and Information | 2019-2020 | LGU Mt. Province |  | On-going
101 | Maintenance of DSEIS (Demographic and Socio-Economic Indicator System) | 2017 onwards Yearly | POPCOM
102 | Quarterly Statwatch | Jan – Dec Quarterly | LGU – Baguio City
103 | Social Protection Research Forum | Annual | DSWD |  | Conducted on 25 December 2018 which was attended by 70 (21 male and 49 female) participants
104 | Dissemination of CBMS Survey Result | May – Dec 2017 3 years | LGU Ifugao |  | Presented the result of the 2016 CBMS Survey to the Sangguniang Panlalawigan (SP) and the Provincial Development Council composed of the chief executives of the different municipalities of Ifugao. Result of this survey is used in the preparation of the Compreshensive Development Program of the province & municipalities & Barangay Development Plans for the barangays. Also in Program designs like the Integrated Development Action Program (IADAP) of the PLGU
105 | Research Forums | SY 2017-2018 (once) | CHED
106 | Research Forums | Yearly | LGU Ifugao |  | Conducted on November 9, 2018 at the PLGU Atrium. This was spearheaded by the Ifugao PSC members in partnership with the PLGU and IFSU. 3 Tourism related researches were presented during this forum.
107 | Data Portal on Environment | 2017 – 2022 Annual updating | DENR
4. Research and Capacity Building
Social
108 | NAPOLCOM PGS, ISO and CSOP Orientation, Cascading, Review | Orientation – 2017 Cascading – 2017-2018 Monitoring – 2018-2022 | NAPOLCOM |  | 18 CSOP Orientations; 11 Crime Prevention Lectures/Career Orientations; 10 PCRM and 10 NCPW activities; 118 Annual Inspection and Audit activities of PNP offices/units regionwide
109 | Assistance for research activities of the NAPOLCOM Central Office | Per request from Central Office | NAPOLCOM |  | Public Perception of Community Safety in Barangays Poblacion, Camp 4, Nangalisan and San Pascual of Tuba; and in Barangays Poblacion, Wangal, Alno and Bahong of La Trinidad (8 localities in Benguet)
110 | Conduct of a Training-Workshop for Public Elementary and Secondary School Heads on Research | April 18-20, 2017 | DEPED
111 | Seminar on Statistics for staff | TBD (once) | CHED
112 | Data Management Training for Sustainable Livelihood Program (SLP) Project Development Officers (PDOs) | March 13-17, 2017 | DSWD |  | Conducted on 25-28 June 2018
113 | Advanced data management training for Pantawid Pamilya Staff | April 4-6, 2017 | DSWD |  | Conducted on 22-25 May 2018 which was attended by 28 Pantawid Pamilya staff
114 | Valuation of Baguio City’s Cultural Heritage Resources | 2018-2019 | UP CSC
115 | Reinforcement of NCIP-CAR ICT | 2018 | NCIP
116 | Training on ICD 10 for Non-Coders | 2018 | DOH |  | 2 batches was conducted, 1 for non coders and 1 for Coders/ Non coders for Abra Province
117 | Training on Effective Presentation of Statistical Report | 2018 | DOH |  | Training for data management was done. Re - planned for 2020
118 | Attendance to Statistics convention, trainings and forums | 2017-2022 | DOH
119 | Tracer Study on Employability of TVET Graduates | Annual | TESDA |  | on-going
120 | ARTA – Report Card Survey | January to December 2017 Semestral | CSC
121 | Statistics Training | 2017-2018 | MGB |  | Basic Statistical Analysis Training conducted Oct. 15-19, 2018; Advance Statistical Analysis Training conducted Nov. 5-9, 2018
122 | Field Health Services Information System version 2018 Roll - out Training | 2018 | DOH |  | Additional activity for 2018. Roll - out was done per province/ city
Economic
123 | Orientation for DTI-CAR staff on the PSA programs/ services related to data generation, storage and management (conduct of surveys, M&E tools, etc.) | 2017 only | DTI |  | Rescheduled on 2019 due to conflicting schedules
124 | Research and extension program of the Provincial Agriculture Office | Jan – Dec Semi-annual/ annual monitoring per crop | LGU Mt. Province |  | On-going data analysis of completed researches (Characterization of Local Rice) Major crop commodities and fishery production consolidated, 2018
125 | Study on Employment in the Tourism Sector |  | DOT
126 | Training of Focal Statistician in the Local Government Units (Municipal level) |  | DOT/ LGUs
127 | Training on the Computation of the Gross Regional Domestic Product | 2018 Annual | LGU Baguio City
128 | Training Seminar techniques and processes in conducting census and data gathering | 2018 Annual | LGU Baguio City
129 | Training Seminar on GRDP DTOI | 2018-2020 | LGU Baguio City
130 | Statistics Seminar/Training | Q4, 2017 Once | DA
131 | Cities and Municipalities Competitiveness Index (CMCI) | 2017 onwards | DTI |  | Survey is done annually
Multi-domain
132 | Capacity – building on Statistical Generation and Analysis Focusing on Environmental Statistics | 2018-2019 | LGU Mt. Province |  | Review on Environmental Code conducted; IEC on Forest Resources and Environmental Management; Training on Applied Geotagging Technology and Web-based Mapping for the Reforestation and Community Identified Watersheds; Training-Workshop on Enhanced Utilization on Recycled Composite Solid Wastes; Conducted Search for the Cleanest and Most-eco friendly delegation during the Provincial Athletic Meet; Provincial Solid Waste Management Board (PSWDB) Meetings conducted
133 | Seminar on Statistics | TBD (once) | CHED
134 | Data Management Training for Sustainable Livelihood Program (SLP) Project Development Officers (PDOs) | March 13-17, 2017 | DSWD |  | Conducted on 25-28 June 2018
135 | Advanced data management training for Pantawid Pamilya Staff | April 4-6, 2017 | DSWD |  | Conducted on 22-25 May 2018 which was attended by 28 Pantawid Pamilya staff
136 | Enhancing and sustaining the capacities of the knowledge and training resource center of UP Baguio on Climate Change and Disaster Risk Reduction and Management | 2018-2019 | UP CSC
137 | Reinforcement of NCIP-CAR ICT | 2017-2022 | NCIP
138 | Training on Effective Presentation of Statistical Report | 2018 | DOH
139 | Attendance to Statistics convention, trainings and forums | 2017 – 2022 | DOH
140 | Training on Data Management | 2018 | DOH
141 | Training on Mineral Accounting | 2017 onwards | DENR/PSA
142 | Validation of Environmental Resources | 2017 onwards | DENR/PSA |  | CAR Environmental and Natural Resources Accounting Project
143 | Impact Analysis of Environment | 2017 onwards | DENR/PSA |  | CAR Environmental and Natural Resources Accounting Project
144 | Training Seminar techniques and processes in conducting census and data gathering | 2018-2020 Annual | LGU Baguio City
145 | Capacity Building on Statistical Tools and Data Management | 2018-2022 Once to twice in a Year | DA
146 | Conduct of Training Workshop/Orientation – GAD Data Base | 2018 | LGU Benguet
147 | Statistics Training | 2017-2018 | MGB |  | Basic Statistical Analysis Training conducted Oct. 15-19, 2018; Advance Statistical Analysis Training conducted Nov. 5-9, 2018
148 | Research Studies | 2018-2022 | LGU Ifugao IFSU |  | 2 trainings were conducted by the PLGU in collaboration with IFSU re; Research Proposal Preparation Training and Data Analysis & Interpretation Training for PSC members and some representatives from the front line services of the PLGU. As a result of these two trainings, two research studies are being conducted by the Provl. Planning & Dev't office (PPDO)and the Ifugao Culture and Heritage Office (ICHO) of the PLGU.
5. Resources in the Regional Statistical System
149 | Establishment of the BSP Economic and Financial Learning Center in Baguio City | 2018 | BSP |  | ongoing construction of the BSP Baguio Barnch
150 | Designation Focal Statistician in the Local Government Units (Municipal level) | proposed | DOT/ LGUs |  | selected municipalities/cities have statistician
*For Status, color-coding as follows:
Implemented/Done in 2018
Started in 2018 and ongoing
Not implemented in 2018
| Submitted by: |  |  |  | Noted by:
| (SGD) VILLAFE P. ALIBUYOG |  |  |  | MILAGROS A. RIMANDO
| Vice-chair, RSC-CAR |  |  |  | RSC Chair, RSC-CAR
| Regional Director, PSA-CAR |  |  |  | Regional Director, NEDA-CAR